## basic
MMD Implementation Checklist: District-Level
District:
Person(s) completing this checklist:
Date:
Focus | Action Steps |  | Current Status (Check 1 level per item) |  |  |  | Planned MMD Focus (Check to identify items for coaching/support, as needed, in each year) |  |  | Notes
|  |  | In place | In progress |  | Not begun | 2018-2019 | 2019-2020 | 2020-2021
|  |  |  | Mid stage | Early stage
Essential Function: District leaders maintain a collaborative culture and climate at the district-level and with building leaders.
Leadership | 1 | Form district leadership team (DLT). (see MMD Blueprint for recommended composition)
| 2 | Designate district-level MMD contact person.
| 3 | Designate building-level MMD contact person (for each building in district) who will disseminate information to faculty and staff in the building.
Communication | 1 | Develop protocol for maintaining ongoing communication with MMD Coaching Support Team Facilitator and CST members, prioritizing the use of virtual technology to increase communication.
| 2 | Develop a district-wide plan for consistent and timely sharing of MMD information with building leaders.
Essential Function: District leaders demonstrate commitment to school improvement through MMD participation in coaching, training, and data-driven action to improve instructional practice.
Commitment | 1 | DLT identify a process for monitoring progress of the MMD practices/components across the 3 years of MMD participation, including annual goals and outcomes, as well as expectations for educator participation in the virtual learning platform in each of the MMD practice areas.
| 2 | Administer Self-Assessment Practice Profile at least twice each year for practices aligning to PD plan.
| 3 | Administer MMD implementation survey (e.g. Collaborative Work Implementation Survey) at least annually.
| 4 | Use technology to increase the quality and timeliness of coaching for improved instruction.
| 5 | Participate in regional, cadre, and state MMD events to gather insights and wisdom from other districts.
Essential Function: District leaders review district-level and building-level instruction and learning outcomes data and provide support based on data
Performance/ Outcomes | 1 | Support the use of MMD data (e.g. SAPP, CWIS) to inform professional development and building-level support.
| 2 | Develop and implement protocol for conducting walk-throughs, observing implementation, and monitoring fidelty and progress toward full implementation of MMD practices across the district.
| 3 | Annually, summarize district-wide fidelity and progress toward full implementation of MMD practices.
| 4 | Establish district- and building-level goal(s) and benchmark(s) performance levels on the SAPP and CWIS.
| 5 | Revisit and revise PD plans based on MMD data.
Essential Function: District leaders align expectations and requirements across the district in order to improve efficiency, consistency, and effectiveness of instruction.
Alignment | 1 | Develop timelines and expectations aligning MMD goals and other district initiatives.
| 2 | Align MMD goals with CSIP: Comprehensive School Improvement Plan.